## Task List
Penn GSE Event Planning Checklist (Sample Only - Add or delete tasks as needed for your specific event)
Task | Who | By When
The basics
Determine your budget
Determine the event design (panel, lecture, discussion, banquet, etc.), including how that will affect the tech & room-set up needs
Determine the event date
Venue
Schedule site visit to confirm space, accessibility, green room, etc.
Get contract/agreement signed with venue
Book extra time before and after the event for set-up and clean-up
Find out if vendor requires a certain caterer
Communicate room set-up to venue contact
Communicate AV/tech needs to venue, if they are providing it
Catering
Get estimates
Choose vendor & request purchase order
Choose final menus
Set up alcohol delivery, if alcohol is being offered
Registration, Marketing & Promotion
Add event to GSE Events calendar and request related webpage updates if needed
Design the email invitation (Mailchimp suggested)
Select & set up registration platform (EventBrite suggested)
Compile invite list: Gather all prospective participant contacts, listservs, etc.
Add video consent language to registration if a recording of the event will be published publicly
Open registration to participants
Track registration and share numbers with project lead
Presenter Communications
Identify & invite presenters to participate
Send Presenter Guidelines
Identify each presenter's tech needs
Gather presenter's session descriptions, bios, headshots
Gather any media (slides, images) that presenters will be using
Schedule a microphone/tech check for each presenter
Share final schedule with presenters (presenter packet)
Travel and Hotel
Suggest hotel space for presenters
Communicate travel reimbursement process to presenters
Choose hotel/book block of room for guests
Promoting your event
Create Penn GSE Events Calendar page
Submit event to AT PENN calendar
Submit event to Inside Penn GSE student newsletter or One Penn GSE Staff/Fac Newsletter, if appropriate
Send an email to all-staff or all-fac listserv if appropriate
Tech planning
Schedule a consult with GSE-IT to review AV needs
Hire an outside AV company if needed
Determine whether you are recording and/or publishing the recording
Gather cell phone numbers for your team to communicate
Run the microphone/tech checks with each presenter
Create a welcome slide to put on screen before event starts
Other Vendors
Hire a photographer and/or videographer and create a shot list
Order signs, flowers, centerpieces or other decorations
Schedules, programs, roles
Create a detailed schedule, spelling out the timing for each activity
Assign roles to team members for event day (staffing)
Create conference program
Order/print table tents, signage, registration materials, nametags, giveaways, etc.
Post-Event Activities
Wrap-up meeting
Send out thank you's and follow-ups
Be sure all invoices are paid
Compile and share takeaways
Archive materials

## Timeline
Penn GSE Event Planning Timeline (Sample Only - Add or delete tasks as needed for your specific event)
8 to 6 months out
Create an event team, hold kickoff meeting
Determine the event design (panel, lecture, discussion, banquet, etc.), including how that will affect the tech & room-set up needs
Determine the event date
Secure a venue that meets your design & tech needs (be sure to do site visits)
Identify & invite presenters to participate
Schedule consult with GSE-IT to talk through tech needs and whether to hire a tech company
Determine your budget
6 to 4 months out
Compile invite list: Gather all prospective participant contacts, listservs, etc.
Design the invitation and registration platform
Send out invitations/registration info/photo consent info
Confirm/finalize presenter list
Arrange for hotel, travel through World Travel
Gather presenter info (bios, photos, session titles) for program & their AV needs
Select caterer and other vendors (photographer, florist, sign company, AV company etc)
Begin promoting your event (add to GSE calendar, AT PENN calendar, etc.)
Do budget check-in to make sure you're on track
12 weeks out
Finalize details with vendors (caterer, photographer, florist)
Finalize the program/schedule for the event
Send out presenter guidelines, including when their mic checks are
Track registration info and share with Project Lead
6 weeks out
Determine staffing for event day
Check in with speakers and confirm final details
Create a conference program
3 weeks out
Create and disseminate a final schedule for internal staff
Print out table tents, signage, registration materials, nametags etc.
Prepare opening/greeting slide(s)
1 week out
Confirm headcount with caterer
Confirm all details with all vendors
Confirm all details with presenters
Confirm all details with staff
Event day
Oversee vendor setup
Walk through the site in advance
Check all mics/AV/tech before guests arrive
Check in with presenters/treat them as VIPs
After Event
Pay all invoices
Debriefing meeting
Send out thank yous and event evaluations
Archive materials